## Feature Tiers
Smart Road Pothole Prioritization System: Feature Tiers
Tier | Meaning | Feature | Maps to problem requirement | Owner | Status
P0 | Must have | Pothole detection on uploaded images | Detect potholes from images/video |  | Not started
P0 | Must have | Size and severity estimate | Estimate size and severity |  | Not started
P0 | Must have | GPS map of detected potholes | Map potholes using GPS |  | Not started
P0 | Must have | Repair priority score | Calculate repair priority score |  | Not started
P0 | Must have | Repair tracker (pending / done) | Track completed and pending repairs |  | Not started
P1 | Important | Traffic density + road importance inputs | Consider traffic density and road importance |  | Not started
P1 | Important | Repeat-damage flag | Identify locations with repeated damage |  | Not started
P1 | Important | Maintenance zone clustering | Group nearby potholes into zones |  | Not started
P2 | Nice to have | Video input (frame sampling) | Detect potholes from images/video |  | Not started
P2 | Nice to have | Repair sequence optimization | Optimize sequence of repair operations |  | Not started
P2 | Nice to have | Road-condition analytics dashboard | Generate road-condition analytics |  | Not started
P3 | Avoid | Auth, microservices, live camera streaming, mobile app | Not required by the problem |  | Not started
Yellow cells = fill in (owner, status). Rule: finish all P0 before real time on P2/P3.

## Architecture
Pipeline: image to repair order
Step | Component | What it does | Approach / tech
1 | Upload | User uploads image + lat/lng | Next.js upload page to API endpoint
2 | Backend API | Receives data, runs pipeline, stores results | Python + FastAPI (SQLAlchemy + psycopg)
3 | Detector | Finds potholes and bounding boxes | Pretrained YOLO pothole model (fine-tune if time allows)
4 | Severity | Maps bbox size to Low / Medium / High | bbox area / image area (detection confidence only filters detections)
5 | Database | Stores potholes, scores, repair status | Supabase (Postgres)
6 | Priority score | Weighted formula over 4 factors | See Priority Score sheet
7 | Zones | Groups nearby potholes | DBSCAN on GPS (K-means as simpler fallback)
8 | Sequence | Orders repairs inside a zone by priority | Greedy nearest-neighbour (skip full TSP)
9 | Map UI | Shows priority map, zones, repair status | Next.js (React + Tailwind) + Leaflet
Caveat: severity is a 2D estimate from the image, not true depth. Say so to judges.

## Priority Score
Priority score model (illustrative, tune before demo)
Factor | Weight
Severity | 0.4
Traffic density | 0.25
Road importance | 0.2
Repeat damage | 0.15
Total (must = 1.00) | 1
Weights check | OK
Assumption: weights are our own starting guess, not from a standard. Blue = editable input.
Example potholes (made-up sample data for demo layout, replace with real detections)
Pothole ID | Severity (0-1) | Traffic (0-1) | Road importance (0-1) | Repeat damage (0-1) | Priority score | Rank | Band
P-001 | 0.9 | 0.8 | 1 | 0.6 | 0.85 | 1 | Critical
P-002 | 0.4 | 0.5 | 0.5 | 0.2 | 0.415 | 4 | Moderate
P-003 | 0.7 | 0.9 | 0.8 | 1 | 0.815 | 2 | Critical
P-004 | 0.2 | 0.3 | 0.3 | 0 | 0.215 | 5 | Low
P-005 | 0.6 | 0.4 | 0.5 | 0.4 | 0.5 | 3 | Moderate
Band thresholds (0.7 / 0.4) are assumptions to tune.

## Tech Choices
Explainable tech choices
Area | Choice | Why (judge-ready) | Simpler alternative / trade-off
Detection | Pretrained YOLO pothole model | Proven for object detection, fast to integrate, disclose in README | Classical CV is simpler but far less accurate
Severity | bbox area ratio to Low/Med/High | Simple, explainable, no depth sensor needed | 2D only; no true depth
Traffic / road importance | Lookup by road type + mock traffic values | Real traffic data is not available in 24h | State clearly that values are mocked
Zones | DBSCAN on GPS | No need to pick cluster count; handles noise | K-means is simpler but needs k
Sequence | Greedy nearest-neighbour by priority | Easy to explain and fast | Not optimal vs full TSP
Backend / DB / Storage | FastAPI + Supabase (Postgres + Storage) | Shared hosted database for the team, real constraints and transactions, free tier | SQLite is simpler but not shared; Supabase needs internet (or a local Postgres) for the demo
Map | Leaflet via react-leaflet | Free, simple, good markers/zones; loaded in the browser only | Google Maps needs API keys
Frontend | Next.js + React + TypeScript + Tailwind CSS | Components, routing and styling out of the box; matches the team's chosen stack | Plain HTML is simpler but harder to organise

## Open Items
Open items (fill in)
Item | Value / answer
Problem release time (YYYY-MM-DD HH:MM)
Submission deadline (YYYY-MM-DD HH:MM)
Team size
Who does ML
Who does backend
Who does frontend
Stack comfort (Python OK?)
GPU / Colab access
Dataset / model chosen
Example: Submission deadline -> 2026-10-08 14:00 (format only, not real)